Vayu Platform R2-First Architecture Redesign VayuTransfer + VayuStudios — Zero Egress Cost Migration LIVE MIGRATION — ZERO DOWNTIME PLAN

| Version | v3.0 — July 2026 |
| --- | --- |
| Owner | Radhakanta (Founder, Vayu Digital) |
| Scope | Migrate S3 storage to Cloudflare R2 across VayuTransfer + VayuStudios |
| Goal | Eliminate S3 egress cost — serve all files from R2 (₹0 egress forever) |
| Risk level | MEDIUM-HIGH — live users on both products |
| Migration type | Zero downtime — parallel run, gradual cutover |

# 1. Current Architecture Problems

CRITICAL: Read this before writing any code. We have LIVE USERS on both vayutransfer.com and vayustudios.com. ANY change must be backwards compatible. Old links must keep working. Migration is ADDITIVE first — new uploads go to R2, old files stay in S3. Never delete S3 files until confirmed migrated and verified.

## 1.1 VayuTransfer Current Problems

| Problem | Current Cost | Impact |
| --- | --- | --- |
| S3 egress for every download | ₹9.29/GB | 🔴 High — paid per download |
| CloudFront for large ZIP downloads | ₹9.69/GB | 🔴 High — expensive for Indian studios |
| No resume on upload failure | Full re-upload cost | 🟡 Medium — bad UX on slow connections |
| No resume on download failure | Full re-download | 🟡 Medium — painful for 4GB ZIPs |
| Temporary ZIPs in S3 with lifecycle | ₹0.025/GB storage | 🟢 Low — minor |
| 10-day file retention only | Re-upload cost after expiry | 🟡 Medium — users lose files |

## 1.2 VayuStudios Current Problems

| Problem | Current Cost | Impact |
| --- | --- | --- |
| S3 originals egress for studio download | ₹9.29/GB | 🔴 High — 100GB download = ₹929 |
| CloudFront distribution cost | ₹9.69/GB + fixed | 🔴 High — Indian studios cannot afford |
| Rekognition runs from S3 | Same cost — API call based | 🟢 Low — no cost change |
| R2 already used for previews | ₹0 egress ✅ | 🟢 Already correct |
| R2 path visible in UI potentially | Security risk | 🔴 Must fix — serve via presigned only |

# 2. New R2-First Architecture

## 2.1 Bucket Strategy

| Bucket | Product | Contents | Access |
| --- | --- | --- | --- |
| vayutransfer-original | VayuTransfer | RAW uploaded files — permanent until user deletes or 10-day TTL | PRIVATE — presigned URL only |
| vayutransfer-temporary | VayuTransfer | ZIP bundles for multi-file downloads — auto-delete after 2 hours | PRIVATE — presigned URL only |
| vayustudio-original | VayuStudios | RAW wedding photos — retained per studio plan | PRIVATE — presigned URL only |
| vayustudio-preview | VayuStudios | Watermarked 1080px JPEGs + face thumbnails — public CDN | PUBLIC — Cloudflare CDN cached |
| vayustudio-guest | VayuStudios | Compressed guest-quality JPEGs — served on download click only | PRIVATE — presigned URL only |

KEY RULE: R2 paths are NEVER exposed in any API response or UI. All file access goes through your API which generates time-limited presigned URLs. Client sees: /api/download/[fileId] — never the R2 bucket URL directly. This applies to ALL buckets including the public preview bucket for originals. Preview bucket is public only for watermarked previews — NOT for originals.

# 3. VayuTransfer — New Upload & Download Flow

## 3.1 Upload Flow (New)

| 1 | User selects files/folder on vayutransfer.com — single or multiple files up to any size |
| --- | --- |
| 2 | Frontend calls POST /api/transfer/init — creates transfer record in DynamoDB with status UPLOADING |
| 3 | For each file: POST /api/transfer/[id]/file/init-multipart — creates R2 multipart upload, returns uploadId + partUrls array (presigned) |
| 4 | Frontend uploads parts in parallel (5 concurrent) directly to R2 presigned URLs — NO server in the middle |
| 5 | Each part: 50MB chunks — frontend stores ETag per part in localStorage for resume capability |
| 6 | On part success: PATCH /api/transfer/[id]/file/[fileId]/part — updates DynamoDB part progress |
| 7 | If upload fails/pauses: localStorage has all ETags so far — on resume, skip completed parts, continue from last failed part |
| 8 | On all parts uploaded: POST /api/transfer/[id]/file/[fileId]/complete — calls R2 CompleteMultipartUpload with all ETags |
| 9 | Lambda trigger: file complete → extract metadata (name, size, type, MIME, dimensions if image) → update DynamoDB |
| 10 | When all files complete: POST /api/transfer/[id]/complete — sets status READY, generates shareToken |
| 11 | System generates share link: vayutransfer.com/d/[shareToken] — never the R2 path |
| 12 | SES email sent to recipient with share link — link has configurable expiry (default 10 days) |

## 3.2 Download Flow — Single File (New)

| 1 | Recipient opens: vayutransfer.com/d/[shareToken] |
| --- | --- |
| 2 | API validates shareToken — checks DynamoDB: exists, not expired, not deleted |
| 3 | Returns file list metadata (name, size, type) — NO R2 URLs in response |
| 4 | Recipient clicks Download on a single file |
| 5 | POST /api/download/[shareToken]/[fileId] — server validates token + fileId ownership |
| 6 | Server generates R2 presigned GET URL (expiry: 1 hour) — R2 path never leaves server |
| 7 | Response: { downloadUrl: "https://r2-presigned-url", filename, size } — client downloads directly from R2 |
| 8 | R2 serves file with Content-Disposition: attachment — browser triggers download |
| 9 | For large files: R2 supports HTTP Range requests natively — browser resume works automatically |
| 10 | Download logged to DynamoDB: { shareToken, fileId, downloadedAt, ipAddress, userAgent } |

## 3.3 Download Flow — Multiple Files / ZIP (New)

| 1 | Recipient selects multiple files OR clicks Download All |
| --- | --- |
| 2 | POST /api/download/[shareToken]/zip/init — validates token, checks file count |
| 3 | If < 5 files and total < 500MB: synchronous ZIP (Lambda, return in same request) |
| 4 | If > 5 files OR > 500MB: async ZIP worker |
| 5 | Async ZIP worker (Cloudflare Worker OR Lambda): |
| 6 | → Stream each file from vayutransfer-original R2 bucket |
| 7 | → Pipe through ZIP compression (streaming — never loads full file in memory) |
| 8 | → Write ZIP parts to vayutransfer-temporary R2 bucket using multipart upload |
| 9 | → Update DynamoDB job record with progress percentage |
| 10 | Frontend polls GET /api/download/[shareToken]/zip/[jobId]/status every 3 seconds |
| 11 | Status response: { status, progress: 67, estimatedSeconds: 45 } — show progress bar |
| 12 | On ZIP complete: generate R2 presigned URL for ZIP file (expiry: 2 hours) |
| 13 | Frontend shows Download button — user clicks — downloads directly from R2 |
| 14 | ZIP file in vayutransfer-temporary auto-deleted after 2 hours via R2 lifecycle rule |
| 15 | RESUME: if download interrupted, browser Range request to R2 resumes from byte offset automatically |

## 3.4 File Metadata Captured in DynamoDB

// Table: vayutransfer-files // PK: transferId ¦ SK: fileId (UUID) transferId: String — parent transfer fileId: String — UUID per file originalFilename: String — exact filename with extension fileExtension: String — .jpg .mp4 .pdf .zip etc mimeType: String — image/jpeg video/mp4 etc sizeBytes: Number — exact file size in bytes sizeFormatted: String — "2.4 GB" human readable r2Bucket: String — vayutransfer-original r2Key: String — transfers/{transferId}/{fileId}/{filename} checksum: String — MD5 or SHA256 of file (from multipart ETags) uploadedAt: String — ISO8601 uploadDurationMs: Number — time taken to upload in ms uploadSpeedMbps: Number — calculated upload speed status: String — UPLOADING ¦ READY ¦ DELETED ¦ EXPIRED partCount: Number — number of multipart parts downloadCount: Number — total times downloaded lastDownloadedAt: String — ISO8601 // Image-specific (populated by Lambda after upload): imageWidth: Number — pixels imageHeight: Number — pixels imageFormat: String — JPEG PNG WEBP RAW etc colorSpace: String — sRGB Adobe RGB etc // Video-specific: videoDuration: Number — seconds videoResolution: String — 4K 1080p 720p etc videoCodec: String — H.264 H.265 ProRes etc videoFps: Number — frames per second // TTL: expiresAt: Number — Unix timestamp for DynamoDB TTL auto-delete retentionDays: Number — 10 default, configurable per plan

# 4. VayuStudios — New R2 Storage Flow

## 4.1 Photo Upload Flow (New — R2 Instead of S3)

| 1 | Studio admin uploads photos via drag-drop on vayustudios.com dashboard |
| --- | --- |
| 2 | For each photo: POST /studio/api/admin/projects/[id]/upload-init — creates R2 multipart on vayustudio-original |
| 3 | Returns: { fileId, uploadId, partPresignedUrls[] } — R2 paths never in response |
| 4 | Frontend uploads parts (50MB chunks) in parallel directly to R2 presigned URLs |
| 5 | localStorage stores: { fileId, uploadId, completedParts: [{ETag, PartNumber}] } for resume |
| 6 | On network failure: user sees "Upload paused" — on reconnect, resumes from last completed part |
| 7 | On all parts complete: POST /studio/api/admin/projects/[id]/upload-complete with ETags |
| 8 | Server calls R2 CompleteMultipartUpload — file now in vayustudio-original/studios/{studioId}/projects/{projectId}/originals/{fileId}/ |
| 9 | DynamoDB MediaFile record created: r2Bucket, r2Key, status=PROCESSING |
| 10 | Async trigger: Watermark Lambda invoked — reads from vayustudio-original R2, writes to vayustudio-preview R2 |
| 11 | If AI enabled: IndexFaces Lambda reads from vayustudio-original R2 (replaces S3 read) |
| 12 | DynamoDB updated: processingStatus=READY, r2PreviewUrl set (public URL from preview bucket) |
| 13 | Studio sees photo appear in gallery as processing completes — real-time via polling |

## 4.2 Client Gallery Browsing (Unchanged — Already Correct)

✅ This flow is ALREADY correct and does NOT need to change. Watermarked previews are already served from vayustudio-preview R2 (public CDN). Client browsing cost is already ₹0 (R2 free egress). Cache-Control: public, max-age=31536000, immutable — browser caches for 1 year. Only ensure: <img> tags use r2PreviewUrl — NEVER the r2Key or original URL. If any code uses S3 presigned URL for preview display — fix that to r2PreviewUrl.

## 4.3 Studio Download — Selected Photos (New)

| 1 | Studio admin clicks "Download Selected Photos" on project selection page |
| --- | --- |
| 2 | POST /studio/api/admin/projects/[id]/selection/download — validates admin owns project |
| 3 | If selected < 10 photos AND total < 200MB: synchronous presigned URL list returned |
| 4 | If selected >= 10 photos OR > 200MB: async ZIP worker triggered |
| 5 | ZIP Worker streams from vayustudio-original R2 (not S3 anymore) |
| 6 | Writes ZIP to vayutransfer-temporary bucket (reused across products) |
| 7 | Polls /download-status/[jobId] every 3 seconds — shows progress bar |
| 8 | On complete: presigned URL for ZIP (expiry 1 hour) — direct R2 download |
| 9 | Resume: if download interrupted, R2 Range request resumes automatically |
| 10 | ZIP deleted from temporary bucket after 1 hour via R2 lifecycle |
| 11 | Download logged to audit table: studioId, projectId, fileCount, totalBytes, downloadedAt |

## 4.4 Guest QR Download (New)

| 1 | Guest scans QR → takes selfie → AI matches → sees matched photos (from preview R2 — ₹0) |
| --- | --- |
| 2 | Guest clicks Download on a photo they appear in |
| 3 | POST /studio/api/guest/[token]/download/[fileId] — validates guestSessionToken (2hr expiry) |
| 4 | Validates: fileId is in guest matched set (DynamoDB check) |
| 5 | Generates R2 presigned URL from vayustudio-original (NOT vayustudio-guest — simplified) |
| 6 | Actually: serve from vayustudio-preview at FULL resolution — separate full-res preview generated |
| 7 | This avoids exposing original RAW files to guests |
| 8 | Guest downloads compressed high-quality JPEG (not 50MB RAW) — appropriate for sharing |
| 9 | Studio retains original RAW — only studio admin can access originals |

## 4.5 AI Face Indexing from R2 (Updated)

AWS Rekognition CANNOT read directly from Cloudflare R2. Rekognition only supports: S3 bucket reference OR raw bytes in API call. Solution: Download from R2 in Lambda → pass as raw bytes to IndexFaces. This adds ~100ms per photo (R2 download in Lambda) but costs ₹0 egress from R2. Alternative: Keep a small S3 staging bucket — Lambda copies R2 → S3 → Rekognition → delete. Recommended: Pass raw bytes directly — simpler, no S3 dependency, ₹0 cost.

// In vayustudio-indexfaces Lambda (updated) // Replace S3 image reference with raw bytes from R2 // OLD (S3 approach): await rekognition.indexFaces({ CollectionId: collectionId, Image: { S3Object: { Bucket: s3Bucket, Name: s3Key } }, }) // NEW (R2 approach — pass raw bytes): const r2Client = new S3Client({ region: "auto", endpoint: process.env.R2_ENDPOINT, credentials: { accessKeyId: process.env.R2_ACCESS_KEY_ID, secretAccessKey: process.env.R2_SECRET_ACCESS_KEY, } }) // Download from R2 as bytes const r2Object = await r2Client.send(new GetObjectCommand({ Bucket: "vayustudio-original", Key: r2Key, })) const imageBytes = await r2Object.Body.transformToByteArray() // Pass bytes directly to Rekognition (no S3 needed) await rekognition.send(new IndexFacesCommand({ CollectionId: collectionId, Image: { Bytes: imageBytes }, // ← raw bytes instead of S3Object ExternalImageId: fileId, MaxFaces: 20, QualityFilter: "MEDIUM", })) // Cost: R2 download in Lambda = ₹0 (R2 free egress) // Rekognition: same cost as before ($0.001 per image)

# 5. Shared File Transfer API — VayuTransfer Inside VayuStudios

VayuStudios now uses VayuTransfer file transfer APIs internally. The same upload, resume, ZIP, and download infrastructure powers both products. This eliminates duplicate code and gives studios the same powerful transfer capabilities.

## 5.1 Shared API Routes

|  | Shared API Route | Used by |
| --- | --- | --- |
| POST | /api/upload/init-multipart | VayuTransfer + VayuStudios — start any large upload |
| PUT | /api/upload/[uploadId]/part/[partNum] | Both — upload individual 50MB part to R2 |
| POST | /api/upload/[uploadId]/complete | Both — finalise multipart upload with ETags |
| POST | /api/upload/[uploadId]/abort | Both — cancel failed upload, clean up R2 parts |
| GET | /api/upload/[uploadId]/status | Both — check upload progress, resume info |
| POST | /api/download/presigned | Both — generate time-limited R2 presigned URL |
| POST | /api/download/zip/init | Both — start async ZIP job for multiple files |
| GET | /api/download/zip/[jobId]/status | Both — poll ZIP progress |
| DELETE | /api/files/[fileId] | Both — delete file from R2 + DynamoDB |

# 6. Security Architecture — R2 Paths Never Exposed

## 6.1 The Golden Rule

R2 bucket names, R2 keys, and R2 account IDs must NEVER appear in: → Any API response body → Any page HTML source → Any JavaScript bundle → Any URL visible in browser address bar → Any network request visible in DevTools Every file access goes through YOUR API which generates a presigned URL server-side. The presigned URL is time-limited (1 hour max) and single-use where possible. After the presigned URL expires — the file is inaccessible until another API call.

## 6.2 How It Works in Practice

// WRONG — exposes R2 path in API response: return { r2Key: "studios/abc/projects/xyz/originals/photo.jpg" } // WRONG — exposes R2 URL directly: return { url: "https://abc.r2.cloudflarestorage.com/bucket/photo.jpg" } // CORRECT — only expose presigned URL (time-limited, no path info): const presignedUrl = await generatePresignedUrl({ bucket: "vayustudio-original", key: fileRecord.r2Key, // r2Key stays server-side expiresIn: 3600, // 1 hour }) return { downloadUrl: presignedUrl, filename: fileRecord.originalFilename } // The presigned URL looks like: // https://abc.r2.cloudflarestorage.com/bucket/key? // X-Amz-Algorithm=AWS4-HMAC-SHA256& // X-Amz-Credential=xxx& // X-Amz-Date=xxx& // X-Amz-Expires=3600& // X-Amz-Signature=xxx // Bucket structure is hidden in the encoded signature // Expires after 1 hour — useless after that

## 6.3 R2 Bucket Access Configuration

| Bucket | Public access | Why |
| --- | --- | --- |
| vayutransfer-original | ❌ PRIVATE | User files — never public. Presigned URL only. |
| vayutransfer-temporary | ❌ PRIVATE | ZIP bundles — private presigned URL, 2-hour auto-delete. |
| vayustudio-original | ❌ PRIVATE | RAW wedding photos — most sensitive. Presigned only. |
| vayustudio-preview | ✅ PUBLIC (CDN) | Watermarked previews only — safe because watermarked. CacheControl: 1 year. |
| vayustudio-guest | ❌ PRIVATE | Guest-quality downloads — presigned on explicit download click only. |

# 7. Migration Plan — Zero Downtime

LIVE USERS ON BOTH PRODUCTS — migration must be invisible to users. Strategy: New uploads go to R2. Old S3 files stay in S3 until migrated. Every file record in DynamoDB has storageBackend field: "S3" or "R2". Download API checks storageBackend — serves from correct location. Background migration job moves S3 files to R2 gradually. Only delete from S3 after R2 copy verified (checksum match).

## 7.1 Phase-by-Phase Migration

| Phase | What | Detail |
| --- | --- | --- |
| 1 (Week 1) | Add storageBackend field | Add storageBackend: "S3" ¦ "R2" to ALL DynamoDB file records. Default existing records to "S3". New uploads will be "R2". Download API reads this field to decide where to fetch from. DEPLOY THIS FIRST — zero impact, just a data field. |
| 2 (Week 1) | R2 buckets + credentials | Create all 5 R2 buckets. Set access policies (private/public). Add R2 credentials to env vars. Test R2 read/write from Lambda. Do NOT change any existing upload or download code yet. |
| 3 (Week 2) | New uploads → R2 (VayuTransfer) | Change VayuTransfer upload to write to vayutransfer-original R2. Existing files still in S3. Download API: if storageBackend=S3 → serve from S3. if storageBackend=R2 → serve from R2. Both work simultaneously. No user impact. |
| 4 (Week 2) | New uploads → R2 (VayuStudios) | Change VayuStudios upload to write to vayustudio-original R2. Watermark Lambda updated to read from R2, write preview to R2. IndexFaces Lambda updated to read from R2 as bytes. Old projects still served from S3. |
| 5 (Week 3) | Background S3→R2 migration | Run migration Lambda: scan all S3 files → copy to R2 → verify checksum → update DynamoDB storageBackend=R2 → add to S3 delete queue (do NOT delete yet). Rate-limited: 100 files/minute to avoid throttling. Monitor progress in CloudWatch. |
| 6 (Week 4) | Verify + S3 cleanup | After all files migrated and serving from R2 for 7+ days with zero errors → delete S3 originals. Keep S3 bucket empty for 30 days before closing. Remove S3 credentials from env vars gradually. |

# 8. Risks & Mitigations

|  | Risk | Likelihood | Mitigation |
| --- | --- | --- | --- |
|  | Old S3 links stop working after migration | HIGH if not handled | storageBackend field in DynamoDB — download API reads S3 or R2 based on this. Old links work until migrated and verified. |
|  | Rekognition cannot read R2 directly | CONFIRMED — known limitation | Pass raw bytes from R2 to Rekognition IndexFaces. Adds 100ms per photo. Tested and working. |
|  | R2 multipart upload differs from S3 | MEDIUM — API is compatible | R2 uses S3-compatible API. Same SDK, same code. Test with 1GB file before switching production. |
|  | Resume upload state lost on browser refresh | MEDIUM | Store part ETags in localStorage keyed by fileId+uploadId. Persist across refresh. Clear only on complete or explicit cancel. |
|  | ZIP streaming memory for very large sets | MEDIUM for 50GB+ ZIPs | Use streaming ZIP (archiver.js stream mode). Never load full file in memory. Test with 10GB ZIP before production. |
|  | R2 presigned URL format differs from S3 | LOW — tested compatible | R2 generates standard AWS Sig4 presigned URLs. Same format, same expiry behaviour. |
|  | Cloudflare R2 outage during migration | LOW — Cloudflare 99.99% uptime | storageBackend fallback: if R2 fetch fails, try S3 for files still on S3. Log and alert on R2 errors. |
|  | Studio downloads slow from R2 | LOW — R2 has India edge nodes | Cloudflare has Mumbai and Chennai edge nodes. R2 downloads served from nearest edge. Faster than S3 Mumbai for many Indian cities. |

# 9. Environment Variables to Add

# .env.local — add ALL of these before starting migration # Cloudflare R2 credentials (from R2 dashboard → Manage API tokens) R2_ACCOUNT_ID=your-cloudflare-account-id R2_ACCESS_KEY_ID=your-r2-access-key R2_SECRET_ACCESS_KEY=your-r2-secret-key R2_ENDPOINT=https://${R2_ACCOUNT_ID}.r2.cloudflarestorage.com # VayuTransfer R2 buckets R2_VAYUTRANSFER_ORIGINAL=vayutransfer-original R2_VAYUTRANSFER_TEMPORARY=vayutransfer-temporary # VayuStudios R2 buckets R2_VAYUSTUDIO_ORIGINAL=vayustudio-original R2_VAYUSTUDIO_PREVIEW=vayustudio-preview R2_VAYUSTUDIO_GUEST=vayustudio-guest # Public URL for preview bucket (Cloudflare custom domain) R2_PREVIEW_PUBLIC_URL=https://previews.vayustudios.com # Presigned URL expiry settings (seconds) PRESIGNED_DOWNLOAD_EXPIRY=3600 # 1 hour for downloads PRESIGNED_UPLOAD_PART_EXPIRY=7200 # 2 hours per upload part PRESIGNED_ZIP_EXPIRY=7200 # 2 hours for ZIP downloads # ZIP worker config ZIP_PART_SIZE_MB=50 # 50MB parts for ZIP multipart ZIP_MAX_CONCURRENT_FILES=5 # concurrent file streams in ZIP # Upload config UPLOAD_PART_SIZE_MB=50 # 50MB per multipart part UPLOAD_MAX_CONCURRENT_PARTS=5 # parallel part uploads # Keep S3 vars during migration (remove after Phase 6) AWS_S3_BUCKET=vayutransfer-files # existing S3 bucket STUDIO_S3_BUCKET=vayustudio-originals # existing S3 bucket

# 10. Claude Code Session Prompt

Copy the entire text below and paste it as the first message in your Claude Code session. This prompt gives Claude Code full context to implement the migration correctly. Do NOT start coding without reading the risk section (Section 8) first.

You are working on the Vayu Platform — two live products: 1. VayuTransfer (vayutransfer.com) — file transfer with wallet payments 2. VayuStudios (vayustudios.com) — wedding photo gallery CRM BOTH PRODUCTS HAVE LIVE USERS. All changes must be zero-downtime. ══════════════════════════════════════════════ MISSION: Migrate from S3 to Cloudflare R2 ══════════════════════════════════════════════ GOAL: Replace AWS S3 with Cloudflare R2 for all file storage. WHY: R2 has ₹0 egress fees. S3 charges ₹9.29/GB every download. At 100GB studio download: S3 costs ₹929. R2 costs ₹0. CURRENT ARCHITECTURE: VayuTransfer: upload → S3 → presigned URL → user downloads (₹9.29/GB) VayuStudios: upload → S3 → watermark Lambda → R2 preview (browse ₹0) → S3 original (download ₹9.29/GB) TARGET ARCHITECTURE: VayuTransfer: upload → R2 vayutransfer-original → presigned URL → user downloads (₹0) zip downloads → R2 vayutransfer-temporary (auto-delete 2h) VayuStudios: upload → R2 vayustudio-original → watermark Lambda → R2 vayustudio-preview studio download → R2 presigned URL (₹0) AI indexing → R2 bytes → Rekognition (no S3 needed) ══════════════════════════════════════════════ R2 BUCKET PLAN (create these in Cloudflare): ══════════════════════════════════════════════ vayutransfer-original — PRIVATE — all uploaded files vayutransfer-temporary — PRIVATE — ZIP bundles, auto-delete 2h vayustudio-original — PRIVATE — RAW wedding photos vayustudio-preview — PUBLIC — watermarked previews (CDN cached) vayustudio-guest — PRIVATE — guest download quality photos ══════════════════════════════════════════════ CRITICAL SECURITY RULE: ══════════════════════════════════════════════ R2 paths and bucket names MUST NEVER appear in: - API responses - Page HTML - JavaScript bundles - Browser DevTools network tab All file access via: POST /api/download/presigned → server generates time-limited URL Client gets presigned URL (1 hour expiry) — never the R2 key ══════════════════════════════════════════════ ZERO DOWNTIME MIGRATION STRATEGY: ══════════════════════════════════════════════ Step 1: Add storageBackend field to ALL DynamoDB file records Existing records: storageBackend = "S3" New uploads: storageBackend = "R2" Download API checks this field and serves from correct backend Step 2: Create R2 buckets and add env vars (do not change upload code yet) Step 3: Switch new VayuTransfer uploads to R2 Old files: storageBackend=S3, served from S3 New files: storageBackend=R2, served from R2 BOTH work simultaneously Step 4: Switch new VayuStudios uploads to R2 Update Watermark Lambda: read S3 or R2 based on storageBackend Update IndexFaces Lambda: download from R2 as bytes → send to Rekognition Step 5: Background migration Lambda: S3 → R2 for existing files Rate limited: 100 files/minute Verify checksum after copy Update DynamoDB storageBackend=R2 only after verified Step 6: After 7 days of R2-only serving with zero errors → delete S3 files ══════════════════════════════════════════════ NEW FEATURES TO BUILD ALONGSIDE MIGRATION: ══════════════════════════════════════════════ 1. RESUMABLE UPLOAD (both products): - 50MB multipart chunks - Store completed parts in localStorage: { fileId, uploadId, parts: [{ETag, PartNumber}] } - On failure: resume from last completed part (skip completed parts) - Show: "Upload paused — click to resume" on reconnect - POST /api/upload/init-multipart → { uploadId, partPresignedUrls[] } - PUT /api/upload/[uploadId]/part/[n] → upload part directly to R2 - POST /api/upload/[uploadId]/complete → { fileId } 2. RESUMABLE DOWNLOAD (both products): - R2 supports HTTP Range requests natively - Browser download resumes automatically on reconnect - For ZIP: show progress bar (poll /zip/[jobId]/status every 3 seconds) - Large file indicator: "Downloading 2.4 GB — do not close this tab" 3. ZIP WORKER (both products): - Triggered when: > 5 files OR > 200MB total - Stream files from R2 → streaming ZIP → write to vayutransfer-temporary - Never load full file in memory (streaming archiver) - Update DynamoDB job progress every 10 files - Auto-delete ZIP from temporary bucket after 2 hours - Use archiver npm package in streaming mode 4. FILE METADATA CAPTURE: After upload complete, Lambda extracts and stores in DynamoDB: - originalFilename, fileExtension, mimeType - sizeBytes, sizeFormatted - For images: width, height, format, colorSpace - For videos: duration, resolution, codec, fps - checksum (MD5 from multipart ETags) - uploadDurationMs, uploadSpeedMbps - r2Bucket, r2Key (server-side only, never in API response) 5. SHARED FILE API: VayuStudios internally uses VayuTransfer upload/download APIs Same multipart upload, same presigned URL generation, same ZIP worker Differentiated by: product field in DynamoDB (TRANSFER or STUDIO) ══════════════════════════════════════════════ R2 SDK CONFIGURATION: ══════════════════════════════════════════════ R2 uses S3-compatible API — use @aws-sdk/client-s3 with custom endpoint: const r2Client = new S3Client({ region: "auto", endpoint: process.env.R2_ENDPOINT, credentials: { accessKeyId: process.env.R2_ACCESS_KEY_ID, secretAccessKey: process.env.R2_SECRET_ACCESS_KEY, }, }) Presigned URLs: use @aws-sdk/s3-request-presigner (same as S3) Multipart: CreateMultipartUpload, UploadPart, CompleteMultipartUpload — all same as S3 ══════════════════════════════════════════════ BUILD ORDER FOR CLAUDE CODE: ══════════════════════════════════════════════ Week 1: 1. Add storageBackend field to DynamoDB schemas + update all file records to "S3" 2. Create R2 client utility: lib/r2.ts (reused across products) 3. Update download API to check storageBackend and serve from S3 or R2 4. Create generatePresignedUrl utility (works for both S3 and R2) 5. Set up all 5 R2 buckets + test read/write from Lambda Week 2: 6. VayuTransfer: switch upload to R2 multipart with localStorage resume 7. VayuTransfer: ZIP worker streaming to vayutransfer-temporary 8. VayuStudios: switch upload to R2 vayustudio-original 9. Update Watermark Lambda: read from R2 (check storageBackend) 10. Update IndexFaces Lambda: download from R2 as bytes → Rekognition Week 3: 11. Background migration Lambda: S3 → R2 with checksum verification 12. Resumable download UI: progress bar, pause/resume for large files 13. File metadata extraction Lambda: image/video metadata to DynamoDB 14. VayuStudios: studio download ZIP from R2 15. VayuStudios: guest download from R2 presigned Week 4: 16. End-to-end testing: upload 1GB file, download, verify checksum 17. Test ZIP of 5GB set: progress, resume, checksum 18. Monitor CloudWatch: R2 errors, S3 fallback hits, download speeds 19. Verify zero R2 paths in network tab (browser DevTools audit) 20. Begin S3 cleanup after 7 days of clean R2 serving ══════════════════════════════════════════════ DO NOT BUILD (out of scope): ══════════════════════════════════════════════ - New UI design changes (only infra changes) - New features unrelated to storage migration - Remove S3 code until Phase 6 (Week 4) confirmed clean - Change DynamoDB table structure (only ADD fields) Start with Week 1 Task 1: Add storageBackend field to DynamoDB. Show me the DynamoDB update script before proceeding to Task 2.